## Worksheet
Logistics Planning - Finance Template (Multi-Page)
Page 1: Overview & Budget Allocation
Project Phase | Budget Allocation (USD) |  |  | Actual Spend (USD) | Variance
| Planning | Transportation | Storage & Handling
Distribution Network Setup | $250,000 | $180,000 | $95,000 | $235,742 | +14,258
Inventory Procurement (Q1) | $310,000 | $95,000 | $78,250 | $326,412 | -16,412
Third-Party Logistics (3PL) Contracts | $85,000 | $75,300 | $24,650 | $81,923 | +3,077
Warehouse Operations (Q1) | $45,000 | $38,560 | $12,420 | $47,893 | -2,893
Total (Page 1) | $690,000 | $455,670 | $210,320 | $691,970 | -1,970
Page 2: Performance Metrics & KPIs
KPI Metric | Target Value | Actual Value | Variance (%) | Status (Green/Yellow/Red)
On-Time Delivery Rate | 98.5% | 96.3% | -2.2% | Yellow
Average Transit Time (Days) | < 4.5 | 4.8 | +6.7%Red | In-Transit Shipment Loss Rate | < 0.2% | 0.35% | +75%Red | Storage Cost per Unit (USD) | $1.20 | $1.38 | +15%Red | Freight Cost as % of Revenue | < 6.0% | 6.7% | +11.7%Red | Inventory Turnover (Annual) | 8.5x | 7.9x | -7.1%Yellow | Overall Performance Score (Weighted Average) | 68% (Red Zone)
Page 3: Forecast & Risk Analysis
Risk Factor | Impact (High/Med/Low) | Probability (High/Med/Low) | Risk Level (RAG) | Action Plan / Mitigation
Port Congestion Delays | High | Medium | Amber (Yellow) | Diversify shipping routes; secure buffer capacity with alternate ports. | Fuel Price Volatility | High | HighRed (High)Negotiate fuel surcharge caps; explore alternative transportation modes. | Labor Shortage at Warehouses | Medium | HighAmber (Yellow)Implement automation; offer retention incentives. | Tariff Changes in Key Markets | High | MediumAmber (Yellow)Maintain compliance team; explore duty optimization strategies. | Downtime in 3PL Partner Systems | Medium | LowGreen (Low)Schedule quarterly system audits; ensure backup integrations. | Natural Disasters Affecting Transport Corridors | High | MediumAmber (Yellow)Create disaster recovery plan; build contingency logistics network. | Total Identified Risks: 6 ¦ High Priority: 3 ¦ Medium: 2 ¦ Low: 1
Page 4: Summary & Recommendations
Summary Item | Description / Status | Next Steps / Recommendations
Budget Efficiency | Slight overspend on Q1 inventory and warehouse operations. | Review procurement timelines; renegotiate storage contracts. | Delivery Performance | On-time rate below target, transit time above benchmark. | Optimize routing algorithms; improve carrier performance tracking. | Risk Exposure | Three high-level risks identified (fuel, port congestion, tariffs). | Develop mitigation strategies with cross-functional teams by Q2. | Technology Utilization | Limited use of predictive analytics and real-time tracking. | Invest in logistics management platform with AI-driven forecasting. | Final Evaluation: Logistics planning is on track but requires corrective actions to improve KPIs and reduce exposure to key risks.