## Worksheet
Project/Activity | Department Responsible | Planned Start Date | Planned End Date | Budget Allocation ($) | Status (Progress %) | Notes / Comments
Purchase of Transport Vehicles | Logistics & Procurement | 2023-10-01 | 2024-01-31 | 75,000.00 | 65% | Delivery delayed by 3 weeks due to supply chain issues.
Fuel & Maintenance Budget - Q4 | Fleet Operations | 2023-10-01 | 2023-12-31 | 45,500.00 | 89% | Maintenance scheduled ahead of time to reduce downtime.
Warehouse Expansion Phase 1 | Facilities Management | 2023-11-01 | 2024-03-31 | 250,000.00 | 45% | Awaiting final permit approval from local authority.
Inventory Management System Upgrade | IT & Logistics Integration | 2023-10-15 | 2024-02-14 | 89,750.00 | 78% | User training sessions planned in January.
Sustainability Initiative: Electric Fleet Pilot | Sustainability Team | 2023-12-01 | 2024-06-30 | 154,300.00 | 35% | Pilot program to assess cost and efficiency over 6 months.
Last Updated:October 20, 2023
Prepared By:Finance Planning Team