## Worksheet
Task ID | Activity Name | Start Date | End Date | Status
T001 | Resource Allocation Planning | 2024-10-01 | 2024-10-15 | In Progress
T002 | Route Optimization Analysis | 2024-10-16 | 2024-11-05 | Not Started
M001 | Initial Planning Review (Milestone) | 2024-10-15 | 2024-10-15 | Completed
T003 | Fleet Capacity Assessment | 2024-11-06 | 2024-11-25 | Not Started
T004 | Supplier Coordination Meeting | 2024-11-26 | 2024-12-10 | Not Started
M002 | Mid-Term Review (Milestone) | 2024-12-10 | 2024-12-10 | Not Started
T005 | Final Logistics Deployment Plan Finalization | 2024-12-11 | 2025-01-31 | Not Started
M003 | Final Planning Approval (Milestone) | 2025-01-31 | 2025-01-31 | Not Started
Legend: