## Worksheet
Logistics Planning - Gantt Chart (Client View)
Project Timeline & Task Progress Overview
Task | Start Date | End Date | Duration (Days) | Progress | Timeline Visualization
Procurement of Materials | 2024-04-01 | 2024-04-15 | 15 | 85% | [███████████▉] April 1 - April 15
Warehouse Preparation | 2024-04-03 | 2024-04-18 | 16 | 65% | [█████████▏] April 3 - April 18
Transportation Booking | 2024-04-05 | 2024-04-19 | 15 | 90% | [███████████▉] April 5 - April 19
Customs Clearance | 2024-04-10 | 2024-04-25 | 16 | 75% | [█████████▋] April 10 - April 25
Final Delivery & Inspection | 2024-04-20 | 2024-05-10 | 21 | 35% | [█████▏] April 20 - May 10
Note:This Gantt chart provides a visual representation of the logistics plan for client review. Progress percentages are updated weekly. Timeline bars are indicative and subject to change based on real-time status.