## Worksheet
Logistics Planning - Gantt Chart Dashboard
Project Timeline & Task Progress Overview
Task / Activity | Start Date | End Date | Duration (Days) | Progress | Responsible Team
Procurement of Materials | 2023-10-05 | 2023-10-18 | 14 |  | Purchasing Dept.
Warehouse Preparation | 2023-10-10 | 2023-10-25 | 16 |  | Facilities Team
Inventory Inbound Kickoff | 2023-10-15 | 2023-10-15 | 0 |  | Operations
Transportation Booking | 2023-10-18 | 2023-10-30 | 13 |  | Logistics Team
Fleet Maintenance & Inspection | 2023-10-20 | 2023-11-05 | 17 |  | Fleet Division
First Delivery Shipment (Pilot) | 2023-11-08 | 2023-11-08 | 0 |  | Delivery Ops.
Tracking & Monitoring Setup | 2023-11-05 | 2023-11-15 | 11 |  | IT & Analytics
Team Training Session | 2023-10-12 | 2023-10-14 | 3 |  | HR & Ops.
Distribution Network Optimization | 2023-11-06 | 2023-11-25 | 20 |  | Supply Chain Analytics
Project Final Review & Handover | 2023-11-30 | 2023-11-30 | 0 |  | Project Office
Legend