## Worksheet
Logistics Planning - Gantt Chart (Data Version)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
T001 | Procurement of Materials | 2023-10-05 | 2023-11-20 | 46 | In Progress | 65%
T002 | Transportation Planning | 2023-11-15 | 2023-11-30 | 16 | In Progress | 85%
T003 | Warehouse Preparation | 2023-11-25 | 2024-01-15 | 51 | Pending | 0%
T004 | Delivery Scheduling | 2024-01-16 | 2024-01-31 | 16 | Pending | 0%
T005 | Final Delivery & Handover | 2024-02-01 | 2024-02-15 | 15 | Pending | 0%
M001 | Project Kick-off | 2023-10-05 | 2023-10-05 | 1 | Completed | 100%
M002 | Final Delivery Completion | 2024-02-15 | 2024-02-15 | 1 | Pending | 0%
Generated on:¦ Logistics Planning - Gantt Chart (Data Version)