## Worksheet
Task | Start Date | End Date | Resource Allocation |  |  |  | Status
|  |  | Team Member | Equipment | Location | Priority
Procurement of Materials | 2024-10-05 | 2024-10-15 | J. Smith | Truck A, Forklift B | Warehouse X | High | In Progress
Transportation Planning | 2024-10-16 | 2024-10-25 | L. Johnson | Truck C, Trailer D | Distribution Hub Y | High | In Progress
Loading & Dispatching | 2024-10-26 | 2024-10-30 | R. Brown | Forklift B, Pallet Juggler E | Warehouse X | Medium | Pending
On-Road Transit (Route A) | 2024-10-31 | 2024-11-07 | T. Davis | Truck C, GPS Tracker F | Route A (X → Z) | High | Pending
Delivery & Unloading (Site Z) | 2024-11-08 | 2024-11-10 | M. Wilson | Forklift B, Pallet Jack G | Site Z Yard | High | Pending
Documentation & Reporting | 2024-11-11 | 2024-11-15 | K. Lee | None | HQ Office | Low | Not Started
Logistics Plan Summary - Total Duration: 40 days ¦ Next Review Date: 2024-10-15