## Worksheet
Logistics Planning - Gantt Chart (Financial View)
Task ID | Task Description | Start Date | End Date | Duration (Days) | Budget Allocated ($) | Budget Spent ($) | Status | Progress (%)
LOG-001 | Procurement of Materials | 2024-03-15 | 2024-04-15 | 31 | 150,000.00 | 97,563.48 | Completed
LOG-002 | Transportation Planning | 2024-03-18 | 2024-05-10 | 53 | 210,500.75 | 68,439.21 | Completed
LOG-003 | Warehouse Setup | 2024-04-01 | 2024-05-15 | 45 | 387,693.88 | 176,942.37 | Completed
LOG-004 | Inventory Management System Integration | 2024-05-16 | 2024-07-31 | 77 | 365,891.56 | 34,891.45 | On Hold (Delayed)
LOG-005 | Final Delivery and Customer Handover | 2024-08-15 | 2024-10-31 | 77 | 498,637.50 | 0 | Pending Start
Total Budget: |  |  |  |  | $1,612,723.69 | $377,836.51