## Worksheet
Logistics Planning - Gantt Chart (Large Business)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | % Complete
LOG-001 | Procurement of Raw Materials | 2024-06-15 | 2024-07-15 | 30 | In Progress
LOG-002 | Production Scheduling | 2024-07-16 | 2024-08-31 | 47 | Scheduled
LOG-003 | Inventory Pre-Loading (Warehouse A) | 2024-08-15 | 2024-09-15 | 31 | Pending
LOG-004 | Transportation Route Planning | 2024-08-15 | 2024-08-31 | 17 | Scheduled
LOG-005 | Loading & Dispatch (Phase 1) | 2024-09-16 | 2024-10-31 | 46 | In Progress
LOG-006 | Delivery Milestone – North Region | 2024-10-15 | 2024-10-15 | 1 | Milestone
LOG-007 | Delivery Milestone – South Region | 2024-11-05 | 2024-11-05 | 1 | Milestone
LOG-008 | Final Quality Inspection & Certification | 2024-11-15 | 2024-11-30 | 16 | Critical Path
Last Updated: June 10, 2024 ¦ Project Version v3.1 ¦ Logistics Planning Gantt Chart (Large Business)