## Worksheet
Logistics Planning - Gantt Chart (Manager View)
Task / Activity | Start Date | End Date | Duration (Days) | Status | Responsible Team | Timeline (Month/Week View)
[6 empty] | Jan 1-7 | Jan 8-14 | Jan 15-21 | Jan 22-28 | Jan 29-Feb 4 | Feb 5-11 | Feb 12-18 | Feb 19-25
Procurement Planning | Jan 01, 2024 | Jan 15, 2024 | 15 | In Progress | Purchasing Team
Vendor Selection | Jan 16, 2024 | Jan 31, 2024 | 16 | In Progress | Purchasing Team
Inventory Setup | Feb 1, 2024 | Feb 10, 2024 | 10 | To Do | Warehouse Team
Transport Logistics | Feb 12, 2024 | Feb 25, 2024 | 14 | To Do | Logistics Team
Final Delivery | Feb 26, 2024 | Mar 1, 2024 | 6 | Milestone (Due) | All Teams
Total Duration |  |  |  |  | 45 Days