## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress
T001 | Route Planning & Approval | 2024-04-05 | 2024-04-12 | 7 | In Progress | 85%
T002 | Carrier Selection & Contracting | 2024-04-13 | 2024-04-19 | 6 | In Progress | 75%
T003 | Inventory Preparation | 2024-04-10 | 2024-04-18 | 8 | In Progress | 95%
T004 | Load & Dispatch (Warehouse) | 2024-04-20 | 2024-04-21 | 1 | Pending | 5%
T005 | Transit Monitoring & Tracking | 2024-04-21 | 2024-04-30 | 9 | Pending | 1%
T006 | Final Delivery & Receipt | 2024-05-01 | 2024-05-15 | 14 | Pending | 0%
M01 | Project Kickoff | 2024-04-05 | 2024-04-05 | 1 | Completed | Milestone
M02 | Final Handover Confirmed | 2024-05-15 | 2024-05-15 | 1 | Pending | Milestone
Total Duration: |  |  |  | 29 days
Prepared for Logistics Planning ¦ Office Use Template ¦ Generated on April 5, 2024