## Worksheet
Logistics Planning - Gantt Chart
Task | Start Date | End Date | Duration (days) | Status | Progress
Procurement of Materials | 2024-03-01 | 2024-03-15 | 15 | In Progress
Warehouse Preparation | 2024-03-10 | 2024-03-18 | 9 | In Progress
Transportation Planning | 2024-03-16 | 2024-03-31 | 16 | Pending
Inventory Receiving | 2024-03-25 | 2024-03-31 | 7 | Pending
Distribution Scheduling | 2024-04-01 | 2024-04-15 | 15 | Pending
Final Delivery Confirmation | 2024-04-15 | 2024-04-15 | 1 | Milestone
Total Duration | 2024-03-01 to 2024-04-15 |  | 46 days