## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team | Status
Procurement of Materials | 2023-10-01 | 2023-10-15 | 15 | Supply Chain | In Progress
Transportation Planning | 2023-10-16 | 2023-10-25 | 10 | Logistics Team | In Progress
Warehouse Preparation | 2023-10-18 | 2023-10-30 | 13 | Operations | Completed
Delivery Scheduling | 2023-10-26 | 2023-11-05 | 10 | Logistics Team | In Progress
Final Inspection & Documentation | 2023-11-06 | 2023-11-10 | 5 | Quality Assurance | Pending
Project Closure & Review | 2023-11-11 | 2023-11-15 | 5 | Project Manager | Pending