## Worksheet
Logistics Planning - Gantt Chart Summary View
Task ID | Task Name | Description | Start Date | End Date | Status
T001 | Procurement Initiation | Begin sourcing of raw materials and components. | 2024-06-01 | 2024-06-15 | In Progress
T002 | Supplier Contracting | Negotiate and finalize contracts with selected suppliers. | 2024-06-16 | 2024-06-30 | In Progress
T003 | Production Scheduling | Create production timelines and allocate resources. | 2024-07-01 | 2024-07-15 | Not Started
T004 | Inventory Preparation | Prepare warehouse and inventory systems for incoming stock. | 2024-07-16 | 2024-07-31 | Not Started
T005 | Transportation Arrangement | Schedule and coordinate delivery routes and carriers. | 2024-08-01 | 2024-08-15 | Not Started
T006 | Delivery & Distribution | Execute delivery plan and monitor distribution network. | 2024-08-16 | 2024-09-30 | Not Started
M101 | Project Kickoff | Official project commencement and team alignment. | 2024-06-01 | 2024-06-01 | Completed
M102 | Final Delivery Complete | All logistics operations concluded and delivered. | 2024-09-30 | 2024-09-30 | Not Started
Note: This Gantt Chart Summary View provides an overview of logistics planning activities with key milestones and timelines.