## Worksheet
Logistics Planning - Team Use Gantt Chart
Task ID | Task Description | Owner | Start Date | End Date | Status | Progress (%)
T001 | Route Planning & Optimization | Alice Johnson | 2023-10-05 | 2023-10-15 | In Progress
T002 | Vehicle Allocation | Robert Smith | 2023-10-16 | 2023-10-25 | To Do
T003 | Driver Scheduling & Training | Sarah Lee | 2023-10-18 | 2023-11-05 | In Progress
T004 | Warehouse Preparation | James Brown | 2023-10-10 | 2023-10-28 | In Progress
T005 | Delivery Timeline Coordination | Lisa White | 2023-10-26 | 2023-11-15 | To Do
T006 | Real-Time Tracking System Setup | David Miller | 2023-11-01 | 2023-11-12 | To Do
T007 | Final Logistics Review | Emily Davis | 2023-11-16 | 2023-11-25 | To Do
Note: This Gantt chart template is designed for team use in logistics planning. Progress bars reflect estimated completion rates.