## Worksheet
Logistics Planning - Gantt Chart Template (Template Version)
Task ID | Task Name | Start Date | End Date | Status | % Complete
001 | Project Initiation | 2024-04-01 | 2024-04-15 | In Progress | 75%
002 | Sourcing & Procurement Planning | 2024-04-16 | 2024-05-15 | In Progress | 60%
003 | Transportation Route Analysis | 2024-05-16 | 2024-06-15 | To Do | 0%
004 | Fleet & Equipment Procurement | 2024-05-16 | 2024-07-31 | In Progress | 50%
005 | Distribution Center Setup | 2024-06-16 | 2024-08-31 | To Do | 5%
006 | Loading & Dispatch Preparation | 2024-09-01 | 2024-09-30 | To Do | 1%
M1 | Project Kickoff Complete | 2024-04-15 | 2024-04-15 | Completed | 100%
M2 | Sourcing Approval Finalized | 2024-05-15 | 2024-05-15 | Completed | 100%
M3 | Fleet Acquisition Confirmed | 2024-07-31 | 2024-07-31 | To Do | 0%
999 | Final Review & Handover | 2024-10-01 | 2024-10-31 | To Do | 0%
Note:This template is designed for logistics planning with a Gantt chart layout. Dates and progress can be updated as required.