## Worksheet
LOGISTICS PLANNING - DETAILED PLANNER TEMPLATE
Project ID | Item Name | Description | Quantity Required | Unit of Measure | Delivery Schedule |  | Status & Tracking
[5 empty] | Planned Date | Actual Date | Status | Notes/Actions
LP-001 | Tyre Assembly Kit | Suspension components for truck chassis | 250 units | Units | 2024-11-15 | — | Pending Shipment | Courier: FedEx; ETA confirmed for 2024-11-20
LP-002 | Refrigerated Container (48 ft) | Cooling unit for perishable goods transport | 10 units | Units | 2024-12-03 | — | In Transit (ETA: 2024-12-05) | Customs clearance in progress; monitored daily
LP-003 | Pallet Rack System | Racking for warehouse storage solution | 15 sets | Sets | 2024-11-28 | — | Pending Installation | Frozen due to warehouse floor prep delay; reschedule required
LP-004 | Battery Pack (Lithium-Ion) | Power supply for electric delivery vehicles | 50 units | Units | 2024-11-20 | 2024-11-23 | Delivered & Inspected (OK) | Passed quality check; inventory update pending
LOGISTICS METRICS SUMMARY
Total Items: |  |  |  | 215 units |  |  |  | On-Time Delivery Rate: 75%
Last Updated: October 26, 2024 ¦ Prepared by Logistics Planning Team ¦ Confidential