## Worksheet
Logistics Planning - Team Use Planner Template
Task ID | Task Description | Assigned To | Department | Start Date | End Date | Status | Prioritization (1-5) | Notes/Comments
T001 | Procure shipping containers | Jane Doe | Logistics | 2024-04-05 | 2024-04-12 | In Progress | 5 | Priority shipment for Q2 delivery.
T002 | Coordinate with trucking partners | Mike Smith | Transportation | 2024-04-06 | 2024-04-15 | To Do | 4 | Schedule pickup and delivery windows.
T003 | Prepare customs documentation | Lisa Chen | Compliance | 2024-04-10 | 2024-04-18 | In Review | 3 | Pending approval from legal.
T004 | Track inventory levels at distribution center | David Lee | Warehouse | 2024-04-12 | Ongoing | In Progress | 5 | Daily updates required.
T005 | Update delivery tracking dashboard | Amanda Wilson | IT & Analytics | 2024-04-13 | 2024-04-17 | To Do | 3 | New integration with logistics API.
Last Updated: April 4, 2024 ¦ Version: v1.0 ¦ Team Use Only