## Worksheet
Logistics Planning - Advanced Project Plan
Task ID | Activity Name | Responsible Party | Start Date | End Date | Status | Budget (USD)(Allocated) | Budget (USD)(Spent) | Progress (%)Actual vs Planned | Risk Level
P01 | Project Initiation & Planning | Logistics Manager | 2025-04-01 | 2025-04-15 | In Progress | $75,0008% | $6,3428.5% | 12%13/12 | Moderate
P02 | Sourcing & Vendor Selection | Procurement Team | 2025-04-16 | 2025-05-15 | On Track | $380,00043% | $129,87634.2% | 41%45/41 | Moderate
P03 | Distribution Network Design & Optimization | Supply Chain Analysts | 2025-04-16 | 2025-06-30 | Critical Delay | $450,00073% | $389,72186.6% | 55%62/55 | High
P04 | Fleet Acquisition & Maintenance Planning | Fleet Manager | 2025-05-01 | 2025-07-15 | On Track | $980,00061% | $434,21844.3% | 65%72/65 | Moderate
P05 | Warehousing & Inventory Strategy Development | Inventory Manager | 2025-06-01 | 2025-07-31 | In Progress | $685,00047% | $319,49346.6% | 52%57/52 | Moderate
P06 | Milestone Review & Approval (Phase 1) | Project Sponsor | 2025-07-15 | 2025-07-31 | Pending | $48,0009% | $4,3129.0% | 75%85/75 | Moderate
P07 | Scheduled Delivery Route Testing (Pilot) | Distribution Coordinator | 2025-08-01 | 2025-08-31 | Not Started | $347,5606% | $19,4785.6% | 0%-/0 | Low
P08 | Technology Integration (WMS/TMS) | IT & Logistics Team | 2025-08-15 | 2025-10-31 | Not Started | $743,48917% | $92,67812.5% | 0%-/0 | Moderate
P09 | Final Project Review & Handover to Operations | CIO / COO Office | 2025-11-01 | 2025-11-30 | Pending | $98,4364% | $3,7893.8% | 0%-/0 | Moderate