## Worksheet
Logistics Planning - Project Plan - Analysis View
Phase | Activity | Start Date | End Date | Duration (Days) | Responsible Team | Status | Budget (USD) | Actual Cost (USD) | Variance (USD)
Phase 1: Planning
1.1 | Define Logistics Requirements | 2024-04-05 | 2024-04-10 | 6 | Planning Team | In Progress | $15,000 | $12,350 | $2,650 (Favorable)
1.2 | Identify Key Suppliers & Partners | 2024-04-11 | 2024-04-18 | 8 | Sourcing Team | Pending Review | $25,000 | $23,150 | $1,850 (Favorable)
Phase 2: Design
2.1 | Design Distribution Network | 2024-04-19 | 2024-05-03 | 15 | Distribution Design Team | In Progress | $85,000 | $79,450 | $5,550 (Favorable)
Phase 3: Implementation
3.1 | Procure Transportation & Warehousing | 2024-05-04 | 2024-05-31 | 28 | Logistics Procurement Team | Pending Review | $350,000 | $347,200 | $2,800 (Favorable)
Phase 4: Optimization
4.1 | Implement Real-Time Tracking System | 2024-06-01 | 2024-06-15 | 15 | Tech Integration Team | In Progress | $75,000 | $73,890 | $1,110 (Favorable)
Phase 5: Review & Close
5.1 | Conduct Performance Audit & Report | 2024-06-16 | 2024-06-30 | 15 | Audit Team & Project Manager | Pending Review | $35,000 | $34,789 | $211 (Favorable)
Total Project | [6 empty] | $680,000 | $651,329 | $28,671 (Favorable)
Note:Status indicators and cost variances reflect data as of May 28, 2024. Project is on track for delivery by June 30, 2024.