## Worksheet
Project Phase | Task Description | Start Date | End Date | Status | Responsible Team/Person | Budget (USD)
Planning & Initiation | Review previous year's logistics performance and identify improvement areas. | 01-Jan-2024 | 15-Jan-2024 | To Do | Logistics Manager, Planning Team | $15,000
Resource Assessment | Evaluate warehouse capacity, transportation needs, and staffing levels. | 16-Jan-2024 | 31-Jan-2024 | To Do | Operations Team, HR Department | $25,000
Route Optimization | Analyze delivery routes for efficiency and cost reduction. | 01-Feb-2024 | 15-Feb-2024 | To Do | Data Analytics Team, Logistics Engineers | $30,000
Supplier Negotiations | Renegotiate contracts with key suppliers and carriers. | 16-Feb-2024 | 28-Feb-2024 | To Do | Purchasing Team, Procurement Manager | $50,000
Inventory Planning | Determine optimal inventory levels by region and product category. | 01-Mar-2024 | 15-Mar-2024 | To Do | Inventory Management Team, Finance Department | $20,000
Risk Assessment & Mitigation | Identify potential risks (weather, supply disruptions) and plan responses. | 16-Mar-2024 | 31-Mar-2024 | To Do | Risk Management Team, Logistics Supervisor | $18,000
Final Plan Approval | Compile all elements into a formal annual logistics plan and seek executive approval. | 01-Apr-2024 | 15-Apr-2024 | To Do | Project Director, Senior Management | $5,000
Total Annual Budget | [5 empty] | $163,000
Note:This template is designed for annual logistics planning and may be adjusted based on organizational needs. Update statuses regularly and ensure cross-functional coordination.