## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Budget (USD)
TASK001 | Finalize logistics strategy and route planning | Logistics Manager | 2024-04-01 | 2024-04-15 | In Progress | 5,000.00
TASK002 | Secure transportation contracts with carriers | Procurement Team | 2024-04-16 | 2024-04-30 | Not Started | 15,000.00
TASK003 | Coordinate warehouse storage and inventory setup | Warehouse Supervisor | 2024-04-18 | 2024-05-10 | In Progress | 8,500.00
TASK004 | Implement tracking and monitoring system | IT Department | 2024-05-11 | 2024-05-25 | Not Started | 6,300.00
TASK005 | Conduct logistics team training and briefing | HR & Training Lead | 2024-05-26 | 2024-06-01 | Not Started | 3,800.00
TASK006 | Execute first full-scale logistics trial run | Logistics Manager | 2024-06-15 | 2024-07-15 | Not Started | 18,750.00
*Note: This project plan is a basic template for logistics planning and can be adjusted based on specific requirements.