## Worksheet
Logistics Planning - Project Plan
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Budget (USD)
LP001 | Route Optimization Analysis | Transportation Team | 2023-10-01 | 2023-10-15 | In Progress | $8,500
LP002 | Warehouse Capacity Assessment | Supply Chain Manager | 2023-10-16 | 2023-10-31 | To Do | $6,200
LP003 | Vendor Contract Negotiation | Purchasing Department | 2023-11-01 | 2023-11-15 | To Do | $4,800
LP004 | Inventory Rebalancing Strategy | Logistics Coordinator | 2023-11-16 | 2023-11-30 | To Do | $7,900
LP005 | Fleet Maintenance Schedule Update | Fleet Operations Team | 2023-12-01 | 2023-12-14 | To Do | $5,600
LP006 | Final Logistics Report Compilation | Project Lead | 2023-12-15 | 2023-12-31 | To Do | $3,500
Total Estimated Budget:$36,500
Project Duration: October 1, 2023 - December 31, 2023