## Worksheet
Logistics Planning - Project Plan (Client View)
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Budget (USD)
LGP-001 | Route Optimization & Feasibility Study | Logistics Team A | 2025-04-01 | 2025-04-15 | In Progress | $18,500
LGP-002 | Supplier Contract Finalization | Procurement Department | 2025-04-16 | 2025-04-30 | Pending | $95,750
LGP-003 | Warehouse Storage Assessment | Facility Management | 2025-04-18 | 2025-05-10 | In Progress | $36,800
LGP-004 | Transportation Provider Selection | Logistics Team B | 2025-05-11 | 2025-05-31 | Pending | $74,900
LGP-005 | Inventory Management System Integration | IT Department | 2025-06-15 | 2025-07-14 | Pending | $143,600
LGP-006 | First Shipment Trial Run (Phase 1) | Operations Team | 2025-07-15 | 2025-07-31 | Pending | $68,450
LGP-007 | Performance Review & Feedback Collection | Project Manager (Client) | 2025-08-15 | 2025-08-31 | Pending | $16,975