## Worksheet
Task ID | Task Name | Responsible Party | Start Date | End Date | Status
T001 | Route Planning & Analysis | Logistics Team | 2024-04-05 | 2024-04-12 | In Progress
T002 | Warehouse Inventory Audit | Supply Chain Ops | 2024-04-13 | 2024-04-15 | Pending
T003 | Vessel Scheduling (Sea Freight) | Marine Logistics | 2024-04-16 | 2024-04-18 | Not Started
T004 | Air Cargo Booking & Dispatch | Air Freight Unit | 2024-04-17 | 2024-04-19 | Not Started
T005 | Customs Documentation Preparation | Compliance Team | 2024-04-18 | 2024-04-21 | Pending
T006 | Final Logistics Coordination Meeting | Project Manager | 2024-04-22 | 2024-04-23 | Pending
T999 | Project Completion & Review | Project Manager | 2024-04-24 | 2024-04-25 | Pending