## Worksheet
Daily Logistics Project Plan
Date | Activity/Task | Responsible Party | Status (Progress) | Notes / Comments
2023-10-01 | Finalize transport routes for delivery zones | Logistics Manager | In Progress | Route optimization in progress; final approval pending.
2023-10-01 | Confirm vehicle availability for week | Fleet Coordinator | Completed | All vehicles confirmed. Backup units on standby.
2023-10-01 | Update delivery schedule with warehouse team | Warehouse Supervisor | Pending Review | Schedule shared; awaiting feedback by 12 PM.
2023-10-02 | Conduct safety briefing for drivers | Operations Lead | Not Started | Scheduled for 9:00 AM at main depot.
2023-10-02 | Inspect all delivery vehicles for maintenance | Maintenance Team | In Progress | 2/5 vehicles completed; remaining scheduled by 3 PM.
2023-10-03 | Coordinate with suppliers for inbound shipment updates | Supply Chain Analyst | Not Started | Awaiting supplier confirmation on delivery windows.
2023-10-03 | Review daily logistics reports from last shift | Logistics Analyst | Completed | No delays reported; minor route deviation noted.
2023-10-04 | Optimize delivery sequences for Zone B and C | Route Planner | Not Started | Pending real-time traffic data.
2023-10-04 | Verify temperature control systems in refrigerated trucks | QA Inspector | In Progress | 3 units tested; remaining 2 to be checked today.
2023-10-05 | Conduct end-of-week logistics performance review | Project Manager | Not Started | Meeting scheduled at 10:00 AM in conference room A.
Total Tasks: |  |  | 10