## Worksheet
Logistics Planning Dashboard - Project Plan
Project: Global Supply Chain Optimization ¦ Status: In Progress ¦ Updated: May 28, 2025
Task ID | Task Name | Responsible Team | Start Date | Due Date | Status | Progress (%)
LP-001 | Route Optimization Analysis | Transportation Team | 2025-05-15 | 2025-06-15 | Ongoing | 78%
LP-002 | Supplier Contract Finalization | Purchasing Department | 2025-05-18 | 2025-06-30 | Ongoing | 64%
LP-003 | Warehouse Automation Upgrade | Operations Team | 2025-05-10 | 2025-06-18 | Delayed | 49%
LP-004 | Inventory Audit Q1 | Warehouse Team | 2025-04-15 | 2025-04-30 | Completed | 100%
LP-005 | Carrier Performance Review | Logistics Coordination | 2025-05-21 | 2025-07-31 | Ongoing | 36%
LP-006 | Customs Clearance Streamlining | Compliance & Legal | 2025-05-14 | 2025-08-31 | Ongoing | 22%
LP-007 | Transportation Cost Benchmarking | Fleet & Finance | 2025-05-12 | 2025-06-31 | Delayed | 8%
LP-008 | Delivery SLA Dashboard Setup | Data Analytics | 2025-04-25 | 2025-05-15 | Completed | 100%