## Worksheet
Logistics Planning - Project Plan - Data Version
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete
Planning Phase
PLN-001 | Define Logistics Requirements | Logistics Manager | 2024-04-05 | 2024-04-10 | In Progress | 75%
PLN-002 | Identify Key Suppliers and Carriers | Sourcing Team | 2024-04-11 | 2024-04-18 | To Do | 0%
PLN-003 | Develop Transportation Strategy | Logistics Analyst | 2024-04-19 | 2024-04-25 | To Do | 0%
Execution Phase
EXE-001 | Procure Transportation Services | Sourcing Team | 2024-04-26 | 2024-05-10 | To Do | 0%
EXE-002 | Setup Warehouse & Distribution Centers | Facility Manager | 2024-05-11 | 2024-05-31 | To Do | 0%
EXE-003 | Implement Tracking & Monitoring System | IT Team | 2024-05-15 | 2024-06-15 | To Do | 0%
Review & Optimization Phase
REV-001 | Conduct Performance Review (KPIs) | Project Manager | 2024-06-16 | 2024-06-30 | To Do | 0%
REV-002 | Optimize Routes & Carrier Mix | Logistics Analyst | 2024-07-01 | 2024-07-15 | To Do | 0%
Final Deliverables & Sign-off
DEL-001 | Submit Final Logistics Plan Report | Project Manager | 2024-07-16 | 2024-07-31 | To Do | 0%
DEL-002 | Obtain Stakeholder Sign-off | Project Sponsor | 2024-08-01 | 2024-08-15 | To Do | 0%