## Worksheet
Logistics Planning Project Plan - Detailed Template
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete | Dependencies(Predecessors) | Budget (USD) | Notes / Comments
T001 | Define Project Scope and Objectives | Project Manager | 2024-04-01 | 2024-04-15 | In Progress | 75% | - | $1,500.00 | Finalize stakeholder alignment.
T002 | Identify Logistics Requirements (Transportation, Warehousing) | Logistics Coordinator | 2024-04-16 | 2024-04-30 | To Do | 0% | T001 | $5,500.00 | Gather data from warehouse and shipping vendors.
T003 | Vendor Selection and Contracting (Carriers & Warehouses) | Procurement Lead | 2024-05-01 | 2024-05-15 | In Progress | 60% | T002 | $8,750.00 | RFQs sent to 12 vendors; shortlist in progress.
T004 | Develop Transportation Network Plan (Routes, Modes) | Network Planner | 2024-05-16 | 2024-05-31 | In Progress | 45% | T003, T001 | $4,890.00 | Optimize for cost and delivery time.
T005 | Design Warehouse Layout and Inventory Flow | Warehouse Manager | 2024-06-01 | 2024-06-15 | To Do | 0% | T003, T018 (Assumed) | $6,250.00 | Include safety and efficiency standards.
T006 | Implement Inventory Management System (Software) | IT Project Lead | 2024-06-16 | 2024-07-15 | To Do | 0% | T015, T033 (Assumed) | $9,875.00 | Integrate with existing ERP.
T007 | Conduct Logistics Simulation & Risk Assessment | Risk Analyst | 2024-07-16 | 2024-08-31 | To Do | 0% | T017, T038 (Assumed)$5,950.00 | Test for disruptions and bottlenecks.
T012 | Training Staff on New Logistics Procedures | HR & Ops Trainer | 2024-09-012024-09-30 | To Do | 15% | T035, T067 (Assumed)$3,150.00 | Develop training materials and sessions.
T112 | Finalize Project Documentation and Handover | Project Manager2024-10-01 | 2024-10-31 | To Do | 5% | T999 (Final)$2,850.00
Total Project Budget: | [7 empty] | $54,715.00
This document is a detailed logistics planning project plan template. Data can be updated as the project progresses.