## Worksheet
Logistics Planning - Project Plan (Editable Template)
Task ID | Task Name | Start Date | End Date | Responsible Party | Status% CompleteNotes/Comments (Editable)
T001Procure Raw Materials2024-04-152024-05-15Supply Chain TeamIn Progress65%Delivery scheduled for May 10th.
T002Transportation Arrangements2024-05-162024-06-30Logistics CoordinatorNot Started0%Awaiting final shipping quotes.
T003Warehouse Receiving Prep2024-06-152024-07-15Warehouse ManagerNot Started0%Final inspection plan needed.