## Worksheet
Employee Name | Role | Task Description | Due Date | Status | Prioritization Level | Progress (%)
Sarah Johnson | Logistics Coordinator | Coordinate inbound shipment for Warehouse A - Q3 delivery | 2024-07-15 | In Progress | High | 65%
Michael Torres | Transport Manager | Finalize route optimization for regional deliveries | 2024-07-18 | In Progress | High | 80%
Emily Chen | Inventory Specialist | Update stock levels for all distribution centers | 2024-07-14 | Completed | Medium | 100%
James Reed | Fleet Supervisor | Inspect and schedule maintenance for 15 delivery trucks | 2024-07-20 | Pending | High | 5%
Linda Park | Supply Chain Analyst | Review carrier performance metrics and report findings | 2024-07-25 | Pending | Medium | 0%
David Mendoza | Warehouse Supervisor | Train new staff on inventory receiving procedures | 2024-07-16 | In Progress | Low | 40%