## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Resource Assigned | Status | Dependencies
LP-001 | Project Initiation | 2024-04-01 | 2024-04-05 | 5 | Project Manager | Pending | N/A
LP-002 | Logistics Requirements Gathering | 2024-04-06 | 2024-04-15 | 10 | Logistics Coordinator | In Progress | LP-001
LP-003 | Vendor Selection and Contracting | 2024-04-16 | 2024-04-30 | 15 | Procurement Officer, Legal Advisor | In Progress | LP-002
LP-004 | Route Planning and Optimization | 2024-05-01 | 2024-05-15 | 15 | Fleet Manager, Data Analyst | Pending | LP-003
LP-005 | Warehouse Preparation and Setup | 2024-05-16 | 2024-06-15 | 31 | Operations Lead, Warehouse Staff | Pending | LP-004, LP-003
LP-006 | Transportation Schedule Finalization | 2024-06-16 | 2024-07-15 | 31 | Fleet Manager, Logistics Planner | Pending | LP-005, LP-004
LP-007 | Inventory and Load Preparation | 2024-07-16 | 2024-08-15 | 31 | Warehouse Team, Quality Inspector | Pending | LP-006, LP-005
LP-008 | First Delivery Execution and Monitoring | 2024-08-16 | 2024-09-30 | 46 | Fleet Drivers, Field Supervisors | Pending | LP-007, LP-006
LP-009 | Performance Review and Reporting | 2024-10-01 | 2024-10-15 | 15 | Data Analyst, Project Manager | Pending | LP-008
LP-010 | Project Closure and Handover | 2024-10-16 | 2024-10-31 | 16 | Project Manager, Stakeholders | Pending | LP-009
Total Duration: |  |  |  | 215 days