## Worksheet
Logistics Planning - Freelancer Project Plan
Task ID | Task Description | Assigned To | Due Date | Status | Budget (USD)
#LP001 | Initial Client Consultation & Requirements Gathering | Jane Doe | 2024-06-15 | In Progress | $850
#LP002 | Route Optimization Analysis & Mapping | Michael Chen | 2024-06-18 | Pending | $1,200
#LP003 | Carrier Selection & Contract Negotiation | Sarah Kim | 2024-06-25 | Pending | $1,500
#LP004 | Customs Documentation Preparation & Compliance Check | James Wilson | 2024-06-28 | Pending | $750
#LP005 | Real-time Tracking System Integration Setup | Lisa Rodriguez | 2024-07-03 | Pending | $1,800
#LP006 | Final Logistics Plan Review & Client Presentation | Jane Doe | 2024-07-05 | Pending | $1,100
Total Project Budget: |  |  |  |  | $7,200