## Worksheet
Logistics Planning - Project Plan
Large Business Style ¦ Version 2.0 ¦ Prepared for: Logistics Department
Project Name:Global Supply Chain Optimization
Status:In Progress
Start Date:January 5, 2024
End Date:June 30, 2024
ID | Task Description | Responsible Party | Start Date | End Date | Status | Priority th
A01 | Conduct supply chain audit across all regions | Logistics Audit Team | 2024-01-05 | 2024-01-31 | In Progress | High
A02 | Identify bottlenecks in current transportation routes | Route Optimization Group | 2024-01-15 | 2024-02-15 | In Progress | High
A03 | Develop new vendor contracts for Tier 1 suppliers | Procurement Department | 2024-02-01 | 2024-03-15 | To Do | High
A04 | Implement real-time shipment tracking system | IT Integration Team | 2024-03-01 | 2024-04-30 | To Do | Medium
A05 | Train warehouse staff on new inventory management protocols | HR & Training Division | 2024-04-15 | 2024-05-15 | To Do | Medium
A06 | Finalize and roll out revised delivery timelines across all regions | Operations Manager | 2024-05-20 | 2024-06-15 | To Do | High
A07 | Conduct post-implementation review and KPI assessment | Project Oversight Committee | 2024-06-16 | 2024-06-30 | To Do | Low
Generated on:April 5, 2024 ¦ Updated Weekly