## Worksheet
Logistics Planning - Project Plan (Manager View)
Phase/Task | Responsible Team | Start Date | End Date | Status | Progress (%) | Prioritization Level
Procure raw materials for Q3 production | Supply Chain Team | 2023-09-01 | 2023-10-15 | In Progress | 78% | High
Prepare warehouse storage zones | Facility Management | 2023-09-05 | 2023-10-10 | In Progress | 65% | High
Secure transportation contracts with carriers | Logistics Coordination | 2023-09-10 | 2023-10-25 | In Progress | 54% | High
Implement inventory tracking system integration | IT & Operations | 2023-09-15 | 2023-11-30 | In Progress | 45% | High
Conduct safety and compliance training sessions | HR & Safety Office | 2023-10-01 | 2023-10-28 | In Progress | 40% | Moderate
Optimize delivery routes for regional hubs | Routing Analytics Team | 2023-10-15 | 2023-11-30 | Delayed (Pending Approval) | 30% | Moderate
Evaluate new supplier proposals for cost efficiency | Procurement & Finance | 2023-10-20 | 2023-11-15 | In Progress | 67% | Moderate
Conduct project-wide review and reporting | Project Management Office | 2023-11-15 | 2023-12-05 | Not Started | 0% | High
Total Tasks:8
Completed:1 (12.5%)
In Progress:6 (75%)
Delayed:1 (12.5%)