## Worksheet
Logistics Planning - Project Plan
Multi-Page Template ¦ Version 1.0 ¦ Prepared for Strategic Logistics Initiative
Date: October 26, 2023
Project Overview
Project Name: | Global Supply Chain Optimization Initiative
Project Manager: | John A. Thompson | Status: | Planning Phase
Start Date: | November 1, 2023 | End Date: | April 30, 2024
Budget: | $1.8M USD | Owner: | Logistics & Operations Department
Task ID | Task Description | Responsible Team | Start Date | End Date | Status
T01 | Conduct Supply Chain Assessment | Logistics Audit Team | 11/01/2023 | 11/30/2023 | In Progress
T02
T03
T04
T05
T06
Final Review & Go-Live PreparationProject Oversight Committee04/01/202404/30/2024To Be StartedPage 1 of 3 ¦ Confidential – For Internal Use OnlyPage 1
Logistics Planning - Project Plan
Multi-Page Template ¦ Version 1.0 ¦ Prepared for Strategic Logistics Initiative
Date: October 26, 2023
Milestone ID | Milestone Title | Target Date | Deliverable | Status
M01 | Supply Chain Assessment Complete | 11/30/2023 | Assessment Report v1.0 | Completed
M02
M03
M04
M05
M06
Resource Type | Role/Position | Team | Dedication (%) | Status
Human Resources | Project Manager | Core Team | 100% | Assigned
Human Resources
Human Resources
Technology
Facilities
External Partners
3PL Provider (Lead)CargoLink Inc.d 100% (Project-dependent)d EngagedPage 2 of 3 ¦ Confidential – For Internal Use OnlyPage 2
Logistics Planning - Project Plan
Multi-Page Template ¦ Version 1.0 ¦ Prepared for Strategic Logistics Initiative
Date: October 26, 2023
Risk ID | Risk Description | Probability | Impact | Mitigation Strategy
R01 | Delay in 3PL Contract Approval by Regulatory Authority | Medium (50%) | Highest (10/10) | Initiate dual sourcing strategy; engage legal advisor early.
R02
R03 | Key Personnel Departure from Core TeamLow (25%) | High (9/10) | Maintain cross-training plans and succession documentation.
R04
R05
Category | Budget (USD) | Spent to Date | Remaining | Status
Personnel Costs (Salaries & Bonuses) | $650,000 | $21,500 | $628,500 | On Track
Technology & Software Licensing
Facility Modifications & Infrastructure
Contractor & 3PL Services
Training & Development
Contingency Reserve (5%)