## Worksheet
Project Name: | Logistics Coordination for Q3 Deliveries
Project Manager: | John Doe
Status: | In Progress
Start Date: | 2024-07-01
End Date: | 2024-09-30
Task ID | Task Description | Responsible Team | Start Date | End Date | Status
L-001 | Route Optimization Analysis | Operations Team | 2024-07-01 | 2024-07-15 | In Progress
L-002 | Vendor Contract Finalization | Procurement Team | 2024-07-10 | 2024-07-31 | To Do
L-003 | Warehouse Capacity Assessment | Logistics Team | 2024-07-15 | 2024-07-31 | In Progress
L-004 | Transportation Provider Onboarding | Supply Chain Team | 2024-07-25 | 2024-08-15 | To Do
L-005 | Distribution Network Simulation | IT & Analytics Team | 2024-08-01 | 2024-08-15 | To Do
L-006 | Real-time Tracking System Integration | IT Team | 2024-08-15 | 2024-08-31 | To Do
L-007 | Final Logistics Strategy Review | Project Steering Committee | 2024-08-31 | 2024-09-15 | To Do
L-008 | Rollout of New Distribution Plan | Field Operations Team | 2024-09-16 | 2024-09-30 | To Do
Note:This is a one-page project plan template for logistics planning. All dates and statuses are subject to change based on actual progress.