## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete
T001 | Initial Logistics Assessment | Logistics Manager | 2025-04-01 | 2025-04-05 | In Progress | 75%
T002 | Route Planning & Optimization | Transportation Coordinator | 2025-04-06 | 2025-04-12 | To Do | 0%
T003 | Warehouse Preparation & Inventory Check | Warehouse Supervisor | 2025-04-13 | 2025-04-17 | To Do | 0%
T004 | Carrier Contracting & Scheduling | Procurement Specialist | 2025-04-18 | 2025-04-21 | To Do | 0%
T005 | Final Logistics Review & Approval | Project Lead | 2025-04-22 | 2025-04-23 | To Do | 0%
Project Summary
|  |  |  | Total Duration: | 23 days