## Worksheet
Logistics Planning - Project Plan - Planning View
Task ID | Task Name | Responsible Party | Start Date | End Date | Status | Milestones |  | Dependencies (Predecessors)
|  |  | Jan 2024 | Feb 2024 |  | Planned | Actual
LGP-001 | Procure Raw Materials | Supply Chain Team | 2024-01-05 | 2024-01-31 | In Progress | Jan 31, 2024 |  | None
LGP-002 | Finalize Transportation Routes | Logistics Coordinator | 2024-01-15 | 2024-01-31 | In Progress | Jan 31, 2024 |  | LGP-001 (Completed)
LGP-003 | Arrange Warehouse Storage | Warehouse Manager | 2024-01-25 | 2024-02-15 | To Do | Feb 15, 2024 |  | LGP-001 (Completed)
LGP-004 | Load & Dispatch Goods | Operations Team | 2024-02-16 | 2024-02-18 | To Do | Feb 18, 2024 |  | LGP-003 (Completed)
|  | Project Duration: | 45 days |  | Total Tasks: | 4 | 0
|  | Timeline Overview: | [LGP-001] ████████████████ ¦ 28 days ¦ [LGP-002] ████████ ¦ 17 days ¦ [LGP-003] ███████████████ ¦ 35 days ¦ [LGP-004] ██ ¦ 3 days ¦
This project plan is updated as of: January 15, 2024