## Worksheet
Logistics Planning - Project Plan (Printable)
Task ID | Task Description | Responsible Team | Start Date | End Date | Status
LPG-001 | Procurement of Transport Vehicles | Logistics Procurement | 2024-04-01 | 2024-04-15 | In Progress
LPG-002 | Route Planning & Optimization | Transportation Planning | 2024-04-16 | 2024-04-30 | To Do
LPG-003 | Warehouse Inventory Setup | Inventory Management | 2024-04-15 | 2024-05-10 | In Progress
LPG-004 | Driver Training & Certification | HR & Operations | 2024-05-11 | 2024-05-25 | To Do
LPG-005 | First Full-Scale Delivery Trial Run | Field Operations | 2024-05-26 | 2024-06-15 | To Do
LPG-006 | Performance Review & Feedback Collection | Project Management Office | 2024-06-16 | 2024-07-15 | To Do
LPG-007 | Final Logistics System Optimization Report | Analytics & Planning | 2024-06-15 | 2024-07-31 | To Do