## Worksheet
Logistics Planning - Project Plan
Project Overview
Task ID | Task Name | Responsible Party | Start Date | End Date | Status | % Complete | Milestone Flag
LP001 | Resource Allocation Planning | Supply Chain Manager | 2024-05-01 | 2024-05-15 | In Progress | 75% | Yes
LP002 | Transportation Route Analysis | Distribution Analyst | 2024-05-16 | 2024-05-31 | Not Started | 0% | No
LP003 | Fleet Maintenance Schedule | Fleet Supervisor | 2024-05-18 | 2024-06-15 | In Progress | 60% | No
LP004 | Warehouse Capacity Assessment | Logistics Coordinator | 2024-05-20 | 2024-06-10 | In Progress | 85% | No
LP005 | Vendor Contract Review | Purchasing Officer | 2024-06-01 | 2024-06-30 | Not Started | 15% | No
Total Tasks: |  | 5
Project Timeline
Project Start:May 1, 2024
Expected Completion:June 30, 2024
Status Summary:On Track – Overall progress at 58%