## Worksheet
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | Budget (USD)
P1001 | Route Analysis & Optimization | Transportation Planning | 2024-05-01 | 2024-05-15 | In Progress | $18,500.00
P1002 | Supplier Onboarding & Contract Finalization | Procurement Team | 2024-05-05 | 2024-05-31 | In Progress | $45,750.00
P1003 | Warehouse Capacity Assessment | Operations Management | 2024-05-10 | 2024-06-15 | To Do | $32,890.00
P1004 | Inventory Forecasting & Replenishment Planning | Data Analytics Team | 2024-05-15 | 2024-06-30 | To Do | $28,450.00
P1005 | Transportation Carrier Selection & Negotiation | Logistics Procurement | 2024-06-01 | 2024-06-30 | To Do | $55,380.00
P1006 | Final Logistics Schedule Validation | Project Management Office | 2024-07-15 | 2024-07-31 | To Do | $15,600.00