## Worksheet
Task ID | Task Name | Start Date | End Date | Responsible Team | Status | Notes
1 | Project Initiation | 2024-04-01 | 2024-04-05 | Logistics Team | Completed | Kick-off meeting held and objectives defined.
2 | Route Planning & Optimization | 2024-04-06 | 2024-04-15 | Operations & Planning | In Progress | Route simulations in progress.
3 | Carrier Selection & Contracting | 2024-04-16 | 2024-04-25 | Procurement Team | Not Started | RFPs issued to potential carriers.
4 | Inventory Audit & Preparation | 2024-04-15 | 2024-04-30 | Warehouse Team | In Progress | Stock levels verified and packaging reviewed.
5 | Transport Coordination & Dispatch | 2024-05-01 | 2024-05-15 | Logistics Coordinator | Not Started | Schedules to be finalized post-contracting.
6 | Delivery & Tracking Monitoring | 2024-05-16 | 2024-05-31 | Tracking Team | Not Started | Real-time tracking system enabled.
7 | Project Closeout & Review | 2024-06-01 | 2024-06-15 | Project Manager | Not Started | Final report and performance evaluation.