## Worksheet
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Budget (USD)
LP-001 | Finalize logistics strategy | Logistics Manager | 2023-10-05 | 2023-10-12 | In Progress | $8,500.00
LP-002 | Identify transportation providers | Procurement Team | 2023-10-13 | 2023-11-17 | To Do | $5,200.00
LP-003 | Negotiate shipping contracts | Contract Manager | 2023-11-18 | 2023-12-15 | In Progress | $4,800.00
LP-004 | Warehouse setup and inventory planning | Operations Team | 2023-11-25 | 2024-12-31 | In Progress | $9,750.00
LP-005 | Implement tracking system integration | IT Department | 2024-01-15 | 2024-03-15 | To Do | $7,300.00
LP-006 | Conduct logistics team training session | HR & Training Lead | 2024-03-18 | 2024-3-31 | To Do | $3,500.00
LP-007 | Monitor and optimize delivery performance | Performance Analyst | 2024-4-15 | 2024-6-31 | To Do | $6,950.00
Total Estimated Budget: | [5 empty] | $46,050.00