## Worksheet
Logistics Planning - Project Plan (Startup)
Task ID | Task Description | Responsible Team | Start Date | End Date | Status
#LP-001 | Define logistics network structure (warehouses, hubs) | Supply Chain Team | 2024-07-15 | 2024-07-31 | In Progress
#LP-002 | Identify and onboard 3 primary carriers | Procurement & Logistics | 2024-07-18 | 2024-08-15 | Pending
#LP-003 | Set up real-time tracking system integration | IT & Operations | 2024-08-01 | 2024-08-31 | Pending
#LP-004 | Develop inventory forecasting model | Data Analytics Team | 2024-08-15 | 2024-09-15 | Pending
#LP-005 | Conduct pilot delivery run (3 cities) | Field Operations | 2024-09-16 | 2024-10-15 | Pending
#LP-006 | Finalize scalability plan for Phase 2 expansion | Strategy & Planning | 2024-10-16 | 2024-11-30 | Pending
Project Start Date: July 15, 2024 ¦ Estimated Completion: November 30, 2024