## Worksheet
Logistics Planning - Project Plan (Summary View)
Task ID | Task Description | Responsible Party | Start Date | End Date | Status
LGP-001 | Initial Logistics Assessment | Logistics Team Lead | 2024-04-01 | 2024-04-15 | In Progress
LGP-002 | Route Planning & Optimization | Transportation Manager | 2024-04-16 | 2024-04-30 | Not Started
LGP-003 | Warehouse Capacity Review | Fulfillment Coordinator | 2024-04-18 | 2024-05-10 | In Progress
LGP-004 | Vendor & Supplier Coordination | Procurement Officer | 2024-05-01 | 2024-05-15 | Not Started
LGP-005 | Transportation Contract Finalization | Logistics Manager | 2024-05-16 | 2024-05-31 | Not Started
LGP-006 | Risk Assessment & Contingency Planning | Risk Analyst | 2024-05-20 | 2024-06-15 | Not Started
Total Duration: |  |  |  |  | 3 months