## Worksheet
Task ID | Task Description | Responsible Team Member(s) | Start Date | End Date | Status | Budget (USD)
LP-001 | Finalize Logistics Strategy & Scope | Project Lead, Ops Manager | 2024-04-05 | 2024-04-15 | In Progress | $5,000.00
LP-002 | Identify & Contract Carriers | Logistics Coordinator, Procurement | 2024-04-16 | 2024-04-30 | To Do | $15,500.00
LP-003 | Secure Warehouse Space & Inventory Prep | Warehouse Manager, Logistics Lead | 2024-04-18 | 2024-05-10 | In Progress | $8,750.00
LP-004 | Develop Tracking & Monitoring System | IT Team, Data Analyst | 2024-05-01 | 2024-05-15 | To Do | $6,300.00
LP-005 | Conduct Team Training & Simulations | Training Manager, Ops Lead | 2024-05-16 | 2024-05-25 | To Do | $3,800.00
LP-006 | Final Audit & Go-Live Preparation | Project Lead, Quality Assurance | 2024-05-26 | 2024-05-31 | To Do | $4,950.00
Total Budget: | [5 empty] | $44,300.00
Note:This project plan is designed for internal team use and will be updated weekly during the planning phase.
Version: 1.0 ¦ Last Updated: April 5, 2024