## Worksheet
Logistics Planning - Project Plan - Tracking View
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | % Complete
TASK-001 | Finalize Supplier Agreements | Procurement Team | 2024-04-05 | 2024-04-15 | In Progress | 65%
TASK-002 | Confirm Warehouse Capacity | Logistics Operations | 2024-04-10 | 2024-04-18 | In Progress | 75%
TASK-003 | Plan Distribution Routes | Routing & Scheduling | 2024-04-12 | 2024-04-25 | Pending | 15%
TASK-004 | Procure Transportation Vehicles | Equipment & Fleet Management | 2024-04-15 | 2024-05-10 | Pending | 5%
TASK-005 | Conduct Safety & Compliance Audit | Compliance Team | 2024-04-18 | 2024-04-30 | Pending | 3%
TASK-006 | Train Logistics Staff | HR & Training | 2024-05-15 | 2024-05-28 | Pending | 1%
TASK-007 | Execute Pilot Run (3 Locations) | Field Operations | 2024-06-15 | 2024-06-30 | Pending | 0%
TASK-008 | Final Review & Approval by Stakeholders | Project Management Office | 2024-07-15 | 2024-07-31 | Pending | 0%