## Worksheet
Project Phase | Activity / Task | Responsible Team | Start Date | End Date | Status | Budget Allocation ($)
Quarter 1 (Jan - Mar)
Planning | Annual Demand Forecasting | Supply Chain Team | 01/05/2024 | 02/15/2024 | In Progress | $85,000.00
Procurement | Supplier Contract Negotiation | Purchasing Department | 01/15/2024 | 02/28/2024 | To-Do
Quarter 2 (Apr - Jun)
Logistics Setup | Warehouse Capacity Assessment | Fulfillment Team | 04/10/2024 | 05/15/2024 | On Hold
Transportation | Schedule Carrier Partnerships | Logistics Coordinator | 04/01/2024 | Pending Approval (Budget Review)
Quarter 3 (Jul - Sep)
Operations | Seasonal Inventory Build-Up | Inventory Management | 07/01/2024 | Not Started
Quarter 4 (Oct - Dec)
Performance Review | Annual Logistics KPI Evaluation | Analytics & Planning | 10/01/2024 | Not Started
Summary Totals
Total Annual Budget: | [5 empty] | $320,000.00