## Worksheet
Logistics Planning - Detailed Project Template
PROJECT OVERVIEW
Project Name: | Logistics Optimization Initiative - Q3 2024
Project Manager: | Jane Doe |  | Start Date: | July 1, 2024 |  | End Date: | September 30, 2024
Department: | Supply Chain & Logistics
LOGISTICS ACTIVITIES & TASKS
Task ID | Activity Description | Responsible Party | Start Date | Due Date | Status | Prioritization Level (1-5) | Budget (USD)
L-001 | Conduct warehouse audit & inventory validation | Warehouse Team Lead - Mike Smith | Jul 1, 2024 | Jul 7, 2024 | Completed | 5 | $3,500
L-002 | Review current carrier contracts and negotiate rates | Procurement Manager - Sarah Johnson | Jul 5, 2024 | Jul 18, 2024 | In Progress | 5 | $12,000
L-003 | Map current supply chain routes and identify bottlenecks | Supply Chain Analyst - Alex Rivera | Jul 8, 2024 | Jul 15, 2024 | Completed | 4 | $5,800
L-004 | Implement real-time shipment tracking system (Software Integration) | IT Logistics Team - David Kim | Jul 16, 2024 | Aug 15, 2024 | In Progress | 5 | $38,900
L-005 | Train field staff on new tracking system and SOPs | Training Coordinator - Lisa Chen | Aug 16, 2024 | Aug 31, 2024 | Pending | 3 | $8,750
L-006 | Conduct pilot test for optimized delivery routes (2 regions) | Logistics Supervisor - James Brown | Aug 1, 2024 | Aug 31, 2024 | In Progress | 5 | $7,500
L-007 | Finalize KPIs and performance dashboard for logistics team | Data Analyst - Emma Wilson | Sep 1, 2024 | Sep 15, 2024 | Pending | 4 | $6,300
TOTAL PROJECT BUDGET: | [6 empty] | $82,750
Notes:All deliverables must be validated by QA team before final sign-off. Any delays in carrier contract negotiations may affect implementation timeline by up to 2 weeks. Risk mitigation plan in place for system rollout.
PROJECT STATUS SUMMARY
Overall Progress: | 65% |  | On Track: | Yes |  | Key Risks: | Contract Delays, System Integration Issues